RailRush Backend

Phase 2 Report: Docker Stack

| Item | Detail |
| --- | --- |
| Project | RailRush: Django seat-reservation backend for Eid-rush booking spikes (target: 35k concurrent users) |
| Phase | 2 of 9: Docker Stack |
| Report date | 17 October 2026 |
| Repository | github.com/MuaazTasawar/railrush-backend (branch: main) |
| Commit | 412a6f6: 9 files changed, 622 insertions, 3 deletions, pushed to origin/main |
| Environment | Windows, PowerShell, Docker 29.7.2 with Compose 5.5.0; Docker Desktop engine with 4 CPUs and about 6.2 GB RAM |
| Result | Security gate 8 of 8 on the second run (the first run caught a configuration leak, section 6); all runtime and container checks passed; 5 findings fixed, 4 risks accepted or open |

# 1. Summary

Phase 2 turned the application into a containerized stack: nginx at the edge, Gunicorn running Django, PgBouncer in front of PostgreSQL 16, Redis 7 and a Celery worker. Only nginx is reachable from the host, and only on 127.0.0.1. Every other container sits on a private network with no route to the internet. The Django image runs as a non-root user with a read-only filesystem and no pip.

The phase also closed three findings from Phase 1 (server banner, trusted-proxy setting, readiness exposure) and moved the database from SQLite to PostgreSQL through PgBouncer. The full 32-test suite now passes inside Docker against real PostgreSQL and Redis.

It was not a clean run, and the report records why. nginx crash-looped for several attempts because of read-only and root-owned temporary folders; a scan found four vulnerabilities in tooling shipped inside the image; and the security gate's first run failed because a local-only setting in .env overrode a production default. Each was diagnosed from real output and fixed. Results below are as reported from the project owner's terminal output. Before delivery, the configuration files were also exercised in isolation on real nginx, Redis, PostgreSQL and PgBouncer outside Docker; those checks supported the design but the Docker results here are the authoritative ones.

# 2. What was built

| File | Purpose |
| --- | --- |
| Dockerfile | Multi-stage build. The runtime image runs as uid 10001, contains no pip and no test files. A separate test target adds dev tools and tests and is never deployed. |
| docker-compose.yml | Seven services plus a test profile. Two networks: edge (published) and backend (internal, no internet). Shared hardening, environment wiring, NUM_PROXIES=1, configurable host port. |
| deploy/gunicorn.conf.py | Process model controlled by environment variables so Phase 8 can compare setups: workers, threads, preload, timeouts, RAM-backed heartbeat directory, path-only access log. |
| deploy/nginx/nginx.conf | Edge proxy: rate and connection limits, body and timeout limits, API Content-Security-Policy, blocked /internal/, restricted readiness, JSON error pages, 1-second micro-cache for public reads, X-Forwarded-For overwritten. |
| deploy/postgres/postgresql.conf | Tuned for the machine budget: durable commits, lock and idle-transaction timeouts, pg_stat_statements, slow-query logging. |
| deploy/redis/redis.conf | Password required, no eviction, append-only persistence, destructive commands disabled. |
| .env.example (rewritten) | Documents the Docker variables, the process-model switches and NGINX_HOST_PORT. |
| .gitattributes (new) | Forces LF line endings so Windows checkouts cannot corrupt mounted config files. |
| scripts/security-check.ps1 (patched) | The deploy check now pins production values, so a local .env cannot hide or fake them. |

The project now contains 98 files.

# 3. Architecture and resource budget

Memory limits total about 4.9 GB, which fits inside the 5.8 GB the Docker engine has. Request path: client, nginx, Gunicorn/Django, PgBouncer, PostgreSQL, with Redis beside Django.

| Service | Image | Memory | Role and key settings |
| --- | --- | --- | --- |
| nginx | nginxinc/nginx-unprivileged:stable-alpine | 256 MB | Only published service (127.0.0.1:8088). Runs as uid 101, read-only filesystem. |
| web | railrush-web (python:3.13-slim-bookworm) | 1536 MB | Gunicorn, 3 workers x 16 threads (WSGI). Read-only, all capabilities dropped, uid 10001. |
| worker | railrush-web | 512 MB | Celery, concurrency 2. Idle until tasks arrive in Phase 7. |
| pgbouncer | edoburu/pgbouncer:v1.26.0-p0 | 128 MB | Transaction pooling: 1000 client connections share 20 server connections (reserve 5, hard cap 40). |
| postgres | postgres:16-alpine | 1536 MB | shared_buffers 512 MB, scram-sha-256, data checksums, synchronous commits. |
| redis | redis:7-alpine | 1 GB | 768 MB maxmemory, no eviction, append-only file, password required. |
| migrate | railrush-web | 512 MB | One-shot: applies migrations directly to PostgreSQL, bypassing PgBouncer, then exits. |

# 4. Key design decisions

| Decision | Rationale | Trade-off |
| --- | --- | --- |
| Private internal network for everything but nginx | A compromised container cannot call out to the internet, and the database and Redis are unreachable from the host. | Containers cannot download anything at runtime; builds happen beforehand. |
| PgBouncer in transaction mode | Thousands of client connections share a small server pool, protecting PostgreSQL. Verified outside Docker: 80 Django threads ran 1,200 transactions with no errors. | No session-level Postgres features; server-side cursors are disabled. |
| Migrations bypass PgBouncer | Schema changes should run on a direct, long-lived connection. | One more connection string to maintain. |
| Redis never evicts | Silently dropping a seat hold would be a correctness bug; a full Redis fails loudly instead. | Capacity must be watched; memory pressure becomes errors, not data loss. |
| Gunicorn threads as the default process model | Simple, measurable, and the same code path as development. ASGI is one environment change away. | Chosen without measurement yet; Phase 8 compares both. |
| nginx overwrites X-Forwarded-For and Django trusts one proxy | A client-supplied header can never become the throttle identity. | Any new proxy in front of nginx requires revisiting NUM_PROXIES. |
| pip removed from the runtime image | Nothing needs it at runtime; its vendored libraries were the only vulnerabilities in the image. | Debugging inside a running container is harder. |
| Read-only root filesystem with RAM-backed writable folders | Malware or a bug cannot persist files in the image. | Each writable path must be declared (this caused the nginx failures). |
| Local stack speaks plain HTTP | No certificate is needed on a laptop. | SECURE_SSL_REDIRECT defaults to false in the local compose file (finding P2-04). |
| Generous per-IP limits at nginx | Mobile carriers put thousands of users behind one address. | Weaker protection against a single abusive address; tuned in Phase 8. |

# 5. Verification results

## Runtime checks (Docker stack, through nginx)

| Check | Observed | Status |
| --- | --- | --- |
| nginx health and identity | healthy; uid=101(nginx); published only on 127.0.0.1:8088 | PASS |
| Liveness through nginx | 200 with {"status": "ok"} | PASS |
| Readiness through nginx | 200 with database: ok, redis: ok (real PostgreSQL via PgBouncer, real Redis) | PASS |
| Metrics blocked at the edge | /internal/metrics returned 404 | PASS |
| Unsafe method rejected | TRACE returned 405 | PASS |
| Headers | Server: nginx with no version; Content-Security-Policy, X-Frame-Options, nosniff, Referrer-Policy and COOP present; responses marked no-store | PASS |
| Redis outage | With Redis stopped: 503 with redis: fail. After restart: 200 | PASS |
| Django database path and proxy trust | Host pgbouncer, port 6432, NUM_PROXIES = 1 | PASS |
| PostgreSQL tuning loaded | shared_buffers 512MB, lock_timeout 5s, data_checksums on | PASS |
| Test suite in Docker | 32 passed in 3.98 s against real PostgreSQL and Redis, no warnings | PASS |
| Web container identity and filesystem | uid=10001(app); touching /app fails: read-only file system; /app contains no .env | PASS |
| nginx filesystem | Writing to /etc/nginx fails: read-only file system | PASS |
| pip absent from the web image | 0 pip entries; 'No module named pip' | PASS |
| Redis authentication | Unauthenticated client received NOAUTH | PASS |
| No internet from app containers | Name resolution failed from the web container (intended) | PASS |
| nginx config test in the running container | syntax is ok; test is successful | PASS |
| Host reachability | 8000 and 6432 closed; nginx port open; 5432 and 6379 open but owned by wslrelay, not RailRush (docker ps shows them unpublished) | NOTE |

## Container security scans

| Scan | Result | Status |
| --- | --- | --- |
| Dockerfile lint (hadolint) | No findings, exit code 0 (on the final Dockerfile) | PASS |
| Trivy configuration scan | Dockerfile: 0 misconfigurations. Only the Dockerfile was recognized; compose and the nginx, Redis and PostgreSQL configs are not covered (P2-07) | NOTE |
| Image scan: railrush-web | 0 HIGH/CRITICAL (4 before pip was removed) | PASS |
| Image scan: nginx-unprivileged | 0 HIGH/CRITICAL | PASS |
| Image scan: PgBouncer | 0 HIGH/CRITICAL | PASS |
| Image scan: postgres:16-alpine | 25 findings, all Go standard-library CVEs in the gosu binary (1 critical, 24 high); accepted, P2-05 | NOTE |
| Image scan: redis:7-alpine | 2 findings: libcrypto3 and libssl3, one OpenSSL fix; accepted, P2-06 | NOTE |

# 6. Security gate results

scripts/security-check.ps1 -Phase 2 ran twice. The first run (10:14 UTC) failed the Django deployment check; after the gate was fixed, the second run (10:18 UTC) passed all eight checks.

| Check | Tool | First run | Second run |
| --- | --- | --- | --- |
| Lint | ruff | PASS | PASS |
| Static analysis | bandit (589 lines, 0 issues) | PASS | PASS |
| Dependency vulnerabilities | pip-audit (project environment) | PASS | PASS |
| Secrets scan | detect-secrets | PASS | PASS |
| Django system check | manage.py check | PASS | PASS |
| Django deployment check | check --deploy, production settings | FAIL | PASS |
| Migration drift | makemigrations --check | PASS | PASS |
| Tests | pytest (32 tests) | PASS | PASS |

Why the first run failed: the Phase 2 bootstrap added SECURE_SSL_REDIRECT=false to the local .env so the plain-HTTP Docker stack works. The gate runs the production settings on the host, and those settings read .env, so the local value overrode the production default and Django warned (security.W008). The settings code itself was correct. The gate now sets the production value explicitly, which a process variable always wins over .env. The separate operational risk, that the local compose file defaults to false, is recorded as P2-04.

# 7. Problems found and fixed during the phase

| Step | What happened | Resolution |
| --- | --- | --- |
| Starting nginx | Port 8080 was already in use by another project's container (alloy-gateway). | Host port made configurable; nginx published on 127.0.0.1:8088. |
| Choosing a PgBouncer image | Docker Hub tag names could not be confirmed in advance. | The bootstrap tried several tags; v1.26.0-p0 pulled and was kept. |
| nginx crash loop, attempt 1 | Exited on every start: could not create /var/cache/nginx/fastcgi_temp on the read-only filesystem. | Gave nginx a RAM-backed /var/cache/nginx. |
| nginx crash loop, attempt 2 | Same folder failed with permission denied: Docker created the RAM disk owned by root. | Both RAM disks (/tmp and /var/cache/nginx) now owned by uid 101. nginx became healthy. |
| PostgreSQL check | An inline psql command failed because Windows PowerShell strips inner double quotes passed to docker. | SQL is piped through standard input instead. |
| Trivy configuration scan | Scanning the whole project over the Windows file share timed out after 14 minutes. | Scan a small temporary copy with a longer timeout. |
| Image scan | 4 HIGH findings in the web image, all vendored inside pip (urllib3, msgpack, setuptools), confirmed from pip's vendor list. | pip removed from the runtime image; rescan clean. |
| Security gate | Deployment check failed because of a local .env value (section 6). | Gate pins production values; second run passed. |

# 8. Findings and observations

| ID | Observation | Risk | Status | Action |
| --- | --- | --- | --- | --- |
| P2-01 | nginx exited on every start: its temp folders failed on the read-only filesystem, then on root-owned RAM disks. | Medium | FIXED | RAM disks owned by uid 101; root filesystem stays read-only. Verified healthy. |
| P2-02 | The runtime image shipped pip, whose vendored libraries carried 4 HIGH vulnerabilities in code the app never runs. | Medium | FIXED | pip removed; rescan shows 0 findings. |
| P2-03 | The gate failed on its first run because .env overrode a production default. | Medium | FIXED | Gate pins production values; passed 8 of 8 on re-run. |
| P2-04 | The local compose file defaults SECURE_SSL_REDIRECT to false. Deployed unchanged to production it would disable the HTTPS redirect. | Medium | OPEN | Phase 9: production compose override and a runbook step requiring true behind TLS. |
| P2-05 | postgres:16-alpine: 25 findings (1 critical), all Go standard-library CVEs inside gosu. | Low | ACCEPTED | gosu only drops privileges once at container start and serves no network traffic. Re-scan after upstream rebuilds; pin the digest in Phase 9. |
| P2-06 | redis:7-alpine: 2 HIGH findings (libcrypto3, libssl3). | Low | ACCEPTED | Redis TLS is not enabled. Pulling the latest image did not change it; re-scan later. |
| P2-07 | Trivy's configuration scan covered only the Dockerfile. | Info | NOTE | Compose and service configs rely on manual review, schema validation and the runtime checks above. |
| P2-08 | Dependencies float (Django 5.2.18, DRF 3.18.3, Celery 5.6.3, gunicorn 25.3.0, redis-py 7.4.1, psycopg 3.3.6, uvicorn 0.54.0) and images use moving tags. | Low | OPEN | Phase 9: hashed lockfile and image digests (continues P0-03). |
| P2-09 | Port 8080 was taken by another project's container. | Info | FIXED | NGINX_HOST_PORT configurable; set to 8088, bound to 127.0.0.1. |
| P2-10 | The Docker engine also runs other projects' containers (labnex-*, alloy-*) that share about 5.8 GB. | Low | NOTE | Stop other stacks before Phase 8 load tests so results are not distorted. |
| P2-11 | Host ports 5432 and 6379 are open, owned by wslrelay (services in a WSL distro), not RailRush. | Info | NOTE | docker ps confirms RailRush publishes only nginx. |
| P2-12 | PgBouncer pool exhaustion currently surfaces as a generic 500; no statement timeout; admin has no static files; TLS and HSTS are off locally. | Low | OPEN | Map exhaustion to 503 with Retry-After, add statement timeouts and static serving after Phase 8 measurements. |
| P2-13 | nginx per-IP limits are generous (100 requests/s; login 5/s with burst 10) because of shared carrier addresses. | Low | NOTE | Tuned with measurements in Phase 8. |
| P2-14 | The terminal's active virtual environment was E:\Goooo\.venv, not the project's, and pip-audit warned. | Info | NOTE | The gate uses the project's interpreter. Activate the project environment before host commands. |

## Phase 1 findings resolved or advanced

| ID | Outcome | Status |
| --- | --- | --- |
| P1-02 | Server banner: responses now carry only 'Server: nginx' with no version; upstream banners are hidden. | CLOSED |
| P1-03 | Proxy trust: NUM_PROXIES=1 is set in compose and confirmed in the running container; nginx overwrites X-Forwarded-For. | CLOSED |
| P1-05 | Readiness: limited to private address ranges at nginx. Verified by configuration test; a denial from a public address cannot be reproduced on a laptop. | CLOSED |
| P1-06 | Throttle counters: the throttle tests now pass against a real shared Redis. Behaviour across several workers under load is verified in Phase 8. | NOTE |

# 9. Not yet covered

- The nginx rate limits and micro-cache were tested in isolation, not through the running stack; they are exercised with real endpoints in Phases 3, 4, 5 and 8.

- End-to-end X-Forwarded-For handling through nginx, Gunicorn and the throttles needs a real endpoint (Phase 3).

- Authentication, brute-force and token-tampering tests (Phase 3); authorization and IDOR tests (Phases 4 and 7); race-condition tests (Phases 6 and 7).

- Dynamic scanning (OWASP ZAP), abuse load tests and the process-model comparison (Phase 8).

- TLS termination, production compose override, hashed lockfile and image digests (Phase 9).

# 10. Next: Phase 3, Accounts API

Phase 3 adds registration, login, token refresh and a profile endpoint on top of the custom user model. It is the first phase with real endpoints behind the full stack, so it will exercise the login throttles (per IP and per account), the nginx auth rate limit and the forwarded-IP chain end to end. Its security gate covers password hashing, token expiry and tampering, brute-force and account-enumeration tests.